## Front Sheet
This workbook provides an evidence-based protocol for assessing whether peat restoration techniques will have an adverse impact on the natural tendency of a blanket peatland to experience slope instability. The workbook is accompanied by a technical report (NatureScot Research Report No 1259, Mills & Rushton, 2023) which details the underlying technical basis for the assessment, though the protocol is designed to be used standalone by Peatland ACTION officers. The protocol comprises three steps in linked worksheets, which should be worked through in order, as follows:
Step 1: | Determine the likelihood of a peat landslide to occur under natural (baseline) conditions, by answering a series of questions that relate to ground conditions at the proposed restoration site.
Step 2: | Determine the impact of proposed restoration techniques on this likelihood by answering a series of questions relating to proposed restoration.
Step 3: | If required, identify potential consequences and associated risks by answering a series of questions about 'receptors' within and adjacent to the site.
At the conclusion of Step 3, it may be necessary to subdivide the restoration site into smaller units (the site is initially considered using 'site average' values in the answer to each question). If this is the case, new versions of the workbook should be created and saved with filenames corresponding to each section. Further information is provided in Chapter 6 of the accompanying report. The 'Summary Form' provides a single page printable summary of inputs and results.
Authored by: OWC Ltd (formerly East Point Geo Ltd), v1.4, 30/03/2024
Change Log
Version | Editor | Description
1.3 | A Mills | Published version pending final NS report number
1.4 | A Mills | Addition of change log, NS report number, minor edits to correct messaging errors and enable full input on Summary Form, no material change to inputs or outputs
Blanket Bog Protocol for Assessing the Potential Impacts of Restoration on Peat Landslide Risk

## 1. Pre-Restoration Likelihood
STEP 1. Calculate the baseline, or "pre-restoration" likelihood of a peat landslide (i.e. the chance of a natural peat slide occurrence in the current site condition)
Please answer ALL the questions below (note that the assessment is not valid unless all entries are completed). | [6 empty] | Answers Required | Likelihood Scores |  | How to answer the question |  | Further Information
[8 empty] | Peat Slide | Bog Burst | If either 'peat slides' or 'bog bursts' are present, enter YES as the answer to question i). |  | Report Section 2.2.1
i) Are there any pre-existing peat landslide scars within the area to be restored or nearby? | [6 empty] | NO | 0 | 0
Is there any evidence of a pre-existing peat slide or bog burst within the area to be restored, on the adjacent hillsides, on the other side of the hill or on the opposing valley side. See "How to answer" for examples.
ii) What is the average peat depth (in m) based on the probes collected from site? | [6 empty] | 0.0 - 0.5 | 0 | 0 | EITHER total the peat depths across all samples and divide by the number of samples (see right) | OR, select a representative peat depth using data from the area to be restored (see right) | Report Section 4.2.1.1
How deep is the peat on average across the area to be developed, if restoration works are to be focused in an area that is not representative of the average peat depth (e.g. in a locally deep area), select a value that corresponds to this area instead. See "How to answer" for further guidance.
If no site specific data are available, the NS Estimated Peat Depth layer within NS GeoView may provide an estimate
iii) What is the average slope angle for the hillside based on elevation data for the site? | [9 empty] | EITHER draw a path in Google Earth and use the "Elevation Profile" tool to read off the "Avg. Slope" value and select the corresponding range in the Gradient (%) box | OR use contours on MagicMap to determine 'rise and run' and enter values in Rise and Run boxes OR enter value from DTM of site | Report Section 4.2.1.2
Enter data for only one of the following:
Enter slope angle: | [5 empty] | Angle: | 0.0 - 2.5 | 1 | 3
Enter the slope angle as a 'gradient' (in %), e.g. if using Google Earth's elevation profile tool: | [5 empty] | Gradient (%): |  | #N/A | #N/A
Enter the 'rise' (elevation change in m) and 'run' (distance in m over which elevation changes): | [5 empty] | Rise: |  | #DIV/0! | #DIV/0! |  |  | For a walk through guide to both Google Earth and MagicMap, click here:
See how to answer for further guidance. | [5 empty] | Run:
Useful links:
https://www.google.co.uk/earth/download/gep/agree.html |  |  | Google Earth Pro download | [8 empty] | GE / MM Guide
https://magic.defra.gov.uk/MagicMap.aspx |  |  | MagicMap online viewer
#DIV/0!
iv) What is the substrate? | [11 empty] | Report Section 4.2.1.4
What is the material immediately underlying the peat (i.e. within a few centimetres) primarily made up of? | [6 empty] | Granular or bedrock | 1 | 1 | EITHER use observations from site (e.g. at the base of the peat profile, as observed in gullies, drains, cuttings, stream margins) | OR refer to BGS "superficial" geology layer in the Open Geology of Britain Viewer. Where 'None recorded', enter 'Unknown' in substrate box
See "How to answer" for further guidance.
Useful links:
http://mapapps.bgs.ac.uk/geologyofbritain/home.html? |  |  | BGS Geology of Britain online viewer
Note that NatureScot internal staff may have access to the NS Geology layer containing equivalent information
v) Which of the following best describes the geomorphology of the peat on site? | [6 empty] | Planar (no other features) | 2 | 2 | EITHER use site observations or refer to the visual glossary of peatland geomorphology to the right: |  | Report Section 2.1
What is the natural geomorphological condition of the area to be restored. This is best determined from either site walkover or review of up-to-date satellite imagery - see "How to answer" for a visual glossary of geomorphological features. | [11 empty] | Report Section 4.2.1.5
vi) Are any of the following land uses present over the area to be restored? | [6 empty] | Other land use | 0 | 0 | EITHER use site observations or refer to the visual glossary of land uses to the right: |  | Report Section 4.2.1.8
What is the primary land use of the area to be restored. This is best determined from site walkover but can also be determined from satellite imagery for some categories of land use.
vii) Which of the following best describes the status and condition of forestry on site? | [6 empty] | Not afforested | 0 | 0 | Refer to the visual glossary or forest status and condition to the right: |  | Report Section 4.2.1.7
If the site is afforested over most of the proposed restoration area, please refer to the "How to answer" guidance in order to classify the alignmentof trees (rows) and present (pre-restoration) status of the forest (e.g. felled or afforested). If the site is part-forested, consider splitting the site into separate protocol workbooks.
viii) Which of the following best describes the slope profile of the area to be restored? | [6 empty] | Rectilinear | 3 | 2 | EITHER draw a path in Google Earth and use the "Elevation Profile" tool to view the profile shape in the main part of the site to be restored OR Use contour spacing on MagicMap to identify the slope profile |  | Report Section 4.2.1.3
What is the slope profile (shape as if 'side on') of the hillslope over which restoration is to be carried out. This can be inferred from changes in contour spacing or using Google Earth's elevation profile tool - see "How to answer" guidance.
For a walk through guide to both Google Earth and MagicMap, click here:
GE / MM Guide
ix) Which of the following best describes artificial drainage in the area to be restored | [6 empty] | Not drained | 0 | 0 | Refer to the visual glossary of drain orientation (right) and use MagicMaps to determine slope direction (from contours). Use the 'majority' of drains to inform the answer. |  | Report Section 4.2.1.6
How are the artificial drains on site arranged in the area to be restored? If the site is afforested, drains will be visible as narrow linear breaks in the treeline, often cross-cutting rows of trees. See "How to answer" guidance to help determine drain orientation.
x) What type of peat is found at the base of the area to be restored | [6 empty] | Fibrous | No scores required |  | Refer to the table to the right to determine the type of peat (requires site observations or field logs of peat character, e.g. using von Post) |  | Report Section 4.3.3.1
The physical composition of the peat at the base of the peat profile (within a few centimetres of its contact with the substrate) provides an indication of its shear strength. Using the simplified descriptions in the "How to answer" guidance, enter the description that best suits the peat observed at site. If no information is entered, the Factor of Safety approach will not be used for comparison.
Based on the landslide susceptibility (contributory factor) approach:
The baseline (pre-restoration) likelihood of a peat landslide is: |  |  |  | LOW |  |  | 8 | 7 | 8
This means that a landslide at the site is: |  |  |  | unlikely given the baseline conditions observed over the restoration area
The most likely form of instability is: |  |  |  | MINOR INSTABILITY
Based on the Factor of Safety approach:
The baseline factor of safety for average site conditions in a fully saturated slope (i.e. ground surface water table) is: | [6 empty] | 22.9086
| Hide these rows | Parameter |  |  | Symbol | Unit | Value
| Hide these rows | Effective cohesion |  |  | c' | kPa | 5
| Hide these rows | Effective angle of internal friction |  |  | φ' | ° | 35
| Hide these rows | Unit weight (peat) |  |  | γ | kN/m3 | 10.5
| Hide these rows | Unit weight (peat, submerged) |  |  | γ' | kN/m3 | 0.69
| Hide these rows | Unit weight (water) |  |  | γw | kN/m3 | 9.81
| Hide these rows | Height of water table / z |  |  | h | m | 1
| Hide these rows | Slope length |  |  | L | m | 500
| Hide these rows | Slope width |  |  | W | m | 100
| Hide these rows | Peat Thickness |  |  | z | m | 0.5
| Hide these rows | Peat Slope Angle |  |  | θ | ° | 2.5
| Hide these rows | Peat Gradient |  |  | grad | ° | #N/A
| Hide these rows | Peat Rise/Run |  |  | r/r | ° | #DIV/0!
| Hide these rows | Slope Angle for Calculation |  |  | θmax | ° | 2.5
| Hide these rows | FOS |  |  | F | - | 22.9086
Hide these rows
Hide these rows
| Hide these rows | Furrow depth |  |  | zf | m | 0.5
| Hide these rows | Crack depth |  |  | zc | m | 0.5
| Hide these rows | Total drawdown depth |  |  | zd | m | 1
| Hide these rows | Tree spatial density (2m separation) |  |  | Td | tree/m2 | 0.44444
| Hide these rows | Tree height |  |  | ht | m | 15
| Hide these rows | Tree diameter |  |  | Øt | m | 0.2
| Hide these rows | Tree density |  |  | γt | kN/m3 | 3.4335
| Hide these rows | Tree root/shoot ratio |  |  | r-s | - | 0.5
| Hide these rows | Tree vertical force |  |  | Ft | kN | 2.427
| Hide these rows | Average tree pressure |  |  | Pt | kPa | 1.0787
| Hide these rows | FOS afforested |  |  | F | - | 6.6305
Google Earth
MagicMap
Google Earth
MagicMap
Note on L163: David Rushton: Based on Linday (2005) indication that cracks can be as much as 70cm
Note on L168: David Rushton: Based on a sikta spruce density of 0.35g/cm3

## 2. Post-restoration Likelihood
STEP 2. Calculate the post-restoration likelihood of a peat landslide, i.e. the effects of restoration groundworks on the natural likelihood
1. Which restoration measures are being adopted?
Select 'YES' or 'NO' for all measures being adopted from the list of restoration techniques below.
For non-afforested bogs only |  |  | Net effect on stability | Score
Ditch-blocking (peat dams) |  |  | n/a
Ditch-blocking (plastic piling dams) |  |  | n/a
Ditch-blocking (wooden or composite dams) |  |  | n/a
Ditch-blocking (drain reprofiling) |  |  | n/a
Ditch-blocking (wave dams) |  |  | n/a
Ditch-blocking (zipping) |  |  | n/a
Deep bunding (trench / backfill) (<20m from bog margin) |  |  | n/a
Cell / surface / fish-scale / scallop / finger bunding |  |  | n/a
Gully reprofiling |  |  | n/a
Gully damming / bunding (stone / surface bunds) |  |  | n/a
Bare peat textile application |  |  | n/a
Bare peat whole turving |  |  | n/a
Bare peat transplanting, seeding or mulching |  |  | n/a
Scrub removal |  |  | n/a
For afforested bogs only:
Forest to bog: tree harvesting |  |  | n/a
Forest to bog: ridge and ditch/furrow blocking |  |  | n/a
Forest to bog: ground smoothing / stump flipping
Stump flipping only |  |  | n/a
Stump flipping and brash incorporation |  |  | n/a
Stump flipping, brash and stem incorporation |  |  | n/a
Ditch-blocking (peat dams) |  |  | n/a
Ditch-blocking (plastic piling dams) |  |  | n/a
Ditch-blocking (wooden or composite dams) |  |  | n/a
Ditch-blocking (drain reprofiling) |  |  | n/a
Ditch-blocking (wave dams and/or zipping) |  |  | n/a
Hidden
|  |  |  | 0 | Modifier for non-ditch blocking non-afforested bogs
|  |  |  | 0 | Modifier for non-ditch blocking afforested bogs
|  |  |  | 0 | Modifier for ditch blocking in afforested or non-afforested bogs
|  |  |  | 8 | Modified likelihood
Based on the landslide susceptibility (contributory factor) approach:
The post-restoration (modified) likelihood of a peat landslide is: |  | LOW
This means that a landslide at the site is: |  | unlikely given the proposed restoration techniques
Based on the factor of safety (limit equilibrium) approach:
The modified factor of safety post-restoration* is: |  |  | 22.9086
* the following techniques are covered in this calculation (note that the 'net effect on stability' comments do not apply to this output):
• gully reprofiling / damming / bunding (by application of buttressing)
• tree harvesting (by change of water table, tree loading and peat density) and ditch/furrow blocking (by application of buttressing)
Hide these tables
Parameter | Symbol | Unit | Value
Effective cohesion | c' | kPa | 5
Effective angle of internal friction | φ' | ° | 35
Unit weight (peat) | γ | kN/m3 | 10.5
Unit weight (peat, submerged) | γ' | kN/m3 | 0.69
Unit weight (water) | γw | kN/m3 | 9.81
Height of water table / z | h | m | 1
Slope length | L | m | 500
Slope width | W | m | 100
Peat Thickness | z | m | 0.5
Peat Slope Angle | θ | ° | 2.5
Peat Gradient | grad | ° | #N/A
Peat Rise/Run | r/r | ° | #DIV/0!
Slope Angle for Calculation | θmax | ° | 2.5
FOS (pre-restoration) | F | - | 22.9086 | 22.9086
Passive earth pressure coefficient | Kp | - | 3.6902
Furrow depth | zf | m | 0.5
Crack depth | zc | m | 0.5
Total drawdown depth | zd | m | 1
Tree spatial density (2m separation) | Td | tree/m2 | 0.44444
Tree height | ht | m | 15
Tree diameter | Øt | m | 0.2
Tree density | γt | kN/m3 | 3.4335
Tree root/shoot ratio | r-s | - | 0.5
Tree vertical force | Ft | kN | 2.427
Average tree pressure | Pt | kPa | 1.0787
FOS (forested) | F | - | 6.6305 | 6.6305
FOS (deforested) | F | - | 6.6305 | 6.6305
FOS (buttressed) | F | - | 22.9933 | 22.9933
FOS (deforested and buttressed) | F | - | 6.6454 | 6.6454
Note on E75: David Rushton: Based on Linday (2005) indication that cracks can be as much as 70cm
Note on E80: David Rushton: Based on a sikta spruce density of 0.35g/cm3

## 3. Consequence and Risk
3. Calculate the consequences should a landslide occur
1. Do "blueline" watercourses occur within 500m of the area to be restored (either on the slope or at its foot)? |  | Hidden | Hidden
If yes, go to next question and if no, go to question 3 | YES | Consequence | PR Likelihood
2. Which of the following statuses applies to the watercourse(s)? (up to and including 5km downstream) |  |  |  | CALCULATED RISK
There is a Private Water Supply in continuous or intermittent use |  |  | LOW | Not yet calculated
There is a Public Water Supply (reservoir) |  |  | LOW | Not yet calculated
There is a designated (SAC, SSSI, SPA, Ramsar) watercourse or connecting watercourse |  |  | LOW | Not yet calculated
The qualifying interests of the designation(s) are likely to be affected by smothering with peat or a short term acid pulse |  |  | LOW | Not applicable
3. Which of the following applies to the terrestrial habitats on site?
Groundwater dependent terrestrial ecosystems (GWDTEs) are present |  |  | LOW | Not yet calculated
There are designated habitats (Natura, SSSI) within or downslope of the proposed restoration area |  |  | LOW | Not yet calculated
The qualifying interests of the designation(s) are likely to be affected by smothering with peat or a direct loss of peat (with overlying habitat) |  |  | LOW | Not yet calculated
4. Which of the following species are observed on or near to site?
European Protected Species (EPS) have been confirmed in restoration area (or within 1km) |  |  | LOW | Not yet calculated
Are the EPS likely to be nesting / resident during restoration works? |  |  | LOW | Not yet calculated
Will the EPS be likely to leave the site permanently if its habitat is disturbed? |  |  | LOW | Not yet calculated
Other vulnerable species have been confirmed in restoration area (or within 1km) |  |  | LOW | Not yet calculated
Vulnerable birds |  |  | LOW | Not yet calculated
Freshwater Pearl Mussels present in watercourse within 5km |  |  | LOW | Not yet calculated
5. Is there a credible runout pathway to any of the following publicly accessible areas within or adjacent to the site?
Footpaths / cycle trails / access track |  |  | LOW | Not yet calculated
Is the footpath / cycle trail / access track used regularly (daily)? |  | HIGH | LOW | Not applicable
Temporarily occupied facility (e.g. hide, building, picnic area, unoccupied farm barn) |  |  | LOW | Not yet calculated
Permanently occupied facility (e.g. house, office, other amenity) |  |  | LOW | Not yet calculated
6. Is there a credible runout pathway to any of the following infrastructure / land uses within or adjacent to the site?
Public road |  |  | LOW | Not yet calculated
Railway line |  |  | LOW | Not yet calculated
Power generation facility (towers, turbines, buried cables, substations, etc) |  |  | LOW | Not yet calculated
Other infrastructure (water supply facility, telecomms facility) |  |  | LOW | Not yet calculated
Grazing / stock (sheep, deer, cattle) |  |  | LOW | Not yet calculated
Arable (standing crops, productive land) |  |  | LOW | Not yet calculated
7. Is there a credible pathway to any of the following historic and/or cultural sites/monuments/buildings within or downslope of site?
Scheduled monument |  |  | LOW | Not yet calculated
Other Nationally Important historic site/building |  |  | LOW | Not yet calculated
Based on the conditions at site prior to restoration and on the proposed restoration techniques, the risk calculated is: |  |  |  | Please answer all questions

## Summary Form
Blanket Bog Protocol for Assessing the Potential Impacts of Restoration on Peat Landslide Risk
Proposal Site: |  | Enter details
Location (NGR): |  | Enter grid reference
Application Year: |  | Enter funding year
Applicant: |  | Enter applicant name
Peatland ACTION Officer: |  | Enter name
Protocol completed by: |  | Enter name
Date Protocol Completed: |  | Enter date completed
Total restoration length (m): |  | 0 - 1,000
Average peat depth (m): |  | 0.0 - 0.5
Likelihood Assessment
The baseline peat landslide likelihood was determined to be: |  |  |  | LOW
The site averaged Factor of Safety was calculated to be: |  |  |  | 22.9086
The following restoration techniques were specified:
(please enter the primary techniques used)
Following specification of restoration techniques
The modified (post-restoration) likelihood was determined to be: |  |  |  |  | LOW
The site averaged modified Factor of Safety was determined to be: |  |  |  |  | 22.9086
Consequence Assessment
Based on the modified likelihood assessment, a consequence assessment: |  |  |  |  | WAS REQUIRED
Receptors were identified as follows (please list):
Risk Assessment
The highest risks were associated with the following receptors (please list, with risks):
Based on the calculated risks, the proposed length of features to be restored and the peat depth: |  |  | Not yet applicable
Approach to Restoration
Replace this text with the rationale for retaining the restoration proposals as supplied (e.g. risks are acceptable, or benefits exceed the potential costs), for adjusting the restoration proposals (e.g. change of technique to reduce risk, or subdivision of site and rejection of parts of site due to Medium risk), or for rejecting the restoration proposals in their current form.
Protocol Filename: | PeatlandACTION Blanket Bog Protocol v1.4 ISSUE - March 2024 Compressed.xlsx

## Drop Down Options (hidden)
DROP DOWN LOOK UP SHEET
This sheet is a reference sheet to which Sheets 1 to 3 refer in order to derive scores for each answered question. The sheet can be modified to reflect revised scoring (if new data or experience suggests this is necessary).
Sheet 1. Pre-Restoration Likelihood | [6 empty] | Sheet 2. Post-restoration likelihood | [5 empty] | Sheet 3. Consequence and Risk |  |  |  | Sheet 4. Summary form
Presence of peat landslide |  |  |  | Peat Slide | Bog Burst | [7 empty] | Presence of watercourse: |  | YES
|  |  | YES | 4 | 4 | [9 empty] | NO
|  |  | NO | 0 | 0
[13 empty] | Status of watercourse/terrestrial habitat: |  | YES |  | Consequence Assessment
[15 empty] | NO |  |  | WAS REQUIRED
Slope Angle |  |  | Slope (°) | Gradient (%) |  |  | Peat Slide | Bog Burst | FOS Value [°] |  |  |  | Watercourse and aquatic habitats |  |  |  |  | WAS NOT REQUIRED
|  |  | 0.0 - 2.5 | 0 | 4.3661 | 0 - 4.4 | 1 | 3 | 2.5 |  |  |  |  | There is a Private Water Supply in continuous or intermittent use | MODERATE
|  |  | 2.5 - 5.0 | 4.3661 | 8.7489 | 4.4 - 8.7 | 1 | 3 | 5 |  |  |  |  | Continuous | MODERATE
|  |  | 5.0 - 7.5 | 8.7489 | 13.1652 | 8.7 - 13.2 | 3 | 2 | 7.5 |  |  |  |  | Intermittent | LOW
|  |  | 7.5 - 10.0 | 13.1652 | 17.6327 | 13.2 - 17.6 | 3 | 1 | 10 |  |  |  |  | NO |  |  |  | 35125 | 70250 | 95250 | 120250 | 145250 | 170250 | 220250
|  |  | 10.0 - 12.5 | 17.6327 | 22.1695 | 17.6 - 22.2 | 3 | 1 | 12.5 |  |  |  |  | There is a Public Water Supply (reservoir) | HIGH |  | Length range (m) | 0.0 - 0.5 | 0.5 - 1.0 | 1.0 - 1.5 | 1.5 - 2.0 | 2.0 - 2.5 | 2.5 - 3.0 | > 3.0
|  |  | 12.5 - 15.0 | 22.1695 | 26.7949 | 22.2 - 26.8 | 3 | 1 | 15 |  |  |  |  | There is a designated (SAC, SSSI, SPA, Ramsar) watercourse or connecting watercourse | LOW |  | 0 - 1,000 | 117.0833 | 117.0833 | 158.75 | 200.4167 | 242.0833 | 283.75 | 367.0833
|  |  | >15.0 | 21.2557 | 0 | > 21.3 | 3 | 1 | ? |  |  |  |  | Designated (SAC, SSSI, Ramsar), with impact | HIGH |  | 1,000 - 5,000 | 23.4167 | 23.4167 | 31.75 | 40.0833 | 48.4167 | 56.75 | 73.4167
[14 empty] | Designated (SAC, SSSI, Ramsar), unlikely impact | MODERATE |  | 5,000 - 10,000 | 11.7083 | 11.7083 | 15.875 | 20.0417 | 24.2083 | 28.375 | 36.7083
Peat Depths |  |  | Thickness [m] | Peat Slide | Bog Burst | FOS Value [m] | Ditches (standard peat dams) | [5 empty] | Terrestrial habitats | Groundwater dependent terrestrial ecosystems (GWDTEs) are present | MODERATE |  | 10,000 - 20,000 | 5.8542 | 5.8542 | 7.9375 | 10.0208 | 12.1042 | 14.1875 | 18.3542
|  |  | 0.0 - 0.5 | 0 | 0 | 0.5 |  |  | Aligned to contour | YES | 1 | Slight reduction in stability |  | Designated (Natura, SSSI), with impact | HIGH |  | 20,000 - 30,000 | 3.9028 | 3.9028 | 5.2917 | 6.6806 | 8.0694 | 9.4583 | 12.2361
|  |  | 0.5 - 1.0 | 2 | 0 | 1 |  |  | Oblique to contour | YES | 1 | Slight reduction in stability |  | Designated (Natura, SSSI), unlikely impact | MODERATE |  | 30,000 - 40,000 | 2.9271 | 2.9271 | 3.9688 | 5.0104 | 6.0521 | 7.0938 | 9.1771
|  |  | 1.0 - 1.5 | 3 | 1 | 1.5 |  |  | Aligned to slope | YES | 0 | Neutral effect on stability | Species | YES |  |  | 40,000 - 50,000 | 2.3417 | 2.3417 | 3.175 | 4.0083 | 4.8417 | 5.675 | 7.3417
|  |  | 1.5 - 2.0 | 1 | 3 | 2 |  |  | Not drained | YES | 0 | Neutral effect on stability |  | NO |  |  | 50,000 - 60,000 | 1.9514 | 1.9514 | 2.6458 | 3.3403 | 4.0347 | 4.7292 | 6.1181
|  |  | 2.0 - 2.5 | 1 | 3 | 2.5 | Ditches (plastic piling) | [9 empty] | 60,000 - 70,000 | 1.6726 | 1.6726 | 2.2679 | 2.8631 | 3.4583 | 4.0536 | 5.244
|  |  | 2.5 - 3.0 | 1 | 3 | 3 |  |  | Aligned to contour | YES | 1 | Slight reduction in stability |  | European Protected Species (EPS) have been confirmed in restoration area (or within 1km) | LOW |  | 70,000 - 80,000 | 1.4635 | 1.4635 | 1.9844 | 2.5052 | 3.026 | 3.5469 | 4.5885
|  |  | 3.0 - 3.5 | 1 | 3 | 3.5 |  |  | Oblique to contour | YES | 1 | Slight reduction in stability |  | Other vulnerable species have been confirmed in restoration area (or within 1km) | LOW |  | 80,000 - 90,000 | 1.3009 | 1.3009 | 1.7639 | 2.2269 | 2.6898 | 3.1528 | 4.0787
|  |  | 3.5 - 4.0 | 1 | 3 | 4 |  |  | Aligned to slope | YES | 1 | Slight reduction in stability |  | Vulnerable birds | MODERATE |  | 90,000 - 100,000 | 1.1708 | 1.1708 | 1.5875 | 2.0042 | 2.4208 | 2.8375 | 3.6708
|  |  | 4.0 - 4.5 | 1 | 3 | 4.5 |  |  | Not drained | YES | 0 | Neutral effect on stability |  | Freshwater Pearl Mussels present in watercourse within 5km | HIGH
|  |  | 4.5 - 5.0 | 1 | 3 | 5 | Ditches (wooden and composite dams) | [9 empty] | Red | Slide impacts may exceed benefits
|  |  | 5.0 - 5.5 | 1 | 3 | 5.5 |  |  | Aligned to contour | YES | 1 | Slight reduction in stability | Public exposure | YES |  |  | Orange | Slide impacts may roughly balance benefits
|  |  | 5.5 - 6.0 | 1 | 3 | 6 |  |  | Oblique to contour | YES | 1 | Slight reduction in stability |  | NO |  |  | Yellow | Benefits likely to exceed slide impacts
|  |  | 6.0 - 6.5 | 1 | 3 | 6.5 |  |  | Aligned to slope | YES | 0 | Neutral effect on stability |  |  |  |  | Light green | Benefits significantly exceed impacts
|  |  | 6.5 - 7.0 | 1 | 3 | 7 |  |  | Not drained | YES | 0 | Neutral effect on stability |  | Footpaths / cycle trails / access track | HIGH |  | Dark green | Impacts negligible relative to benefits
|  |  | 7.0 - 7.5 | 1 | 3 | 7.5 | Ditches (reprofiling / wave dams / zipping) | [6 empty] | Temporarily occupied facility (e.g. hide, building, picnic area, unoccupied farm barn) | HIGH
|  |  | 7.5 - 8.0 | 1 | 3 | 8 |  |  | Aligned to contour | YES | 1 | Slight reduction in stability |  | Permanently occupied facility (e.g. house, office, other amenity) | VERY HIGH
|  |  | 8.0 - 8.5 | 1 | 3 | 8.5 |  |  | Oblique to contour | YES | 1 | Slight reduction in stability
|  |  | 8.5 - 9.0 | 1 | 3 | 9 |  |  | Aligned to slope | YES | 0 | Neutral effect on stability | Infrastructure | YES
|  |  | 9.0 - 9.5 | 1 | 3 | 9.5 |  |  | Not drained | YES | 0 | Neutral effect on stability |  | NO
|  |  | 9.5 - 10.0 | 1 | 3 | 10
[7 empty] | Trench / backfill bunding |  |  | YES | 2 | Reduction in stability |  | Public road | HIGH
Substrate Geology |  |  | Substrate | Peat Slide | Bog Burst | [8 empty] | Railway line | VERY HIGH
|  |  | Cohesive (clay) or iron pan | 3 | 3 |  | Cell / surface bunding |  |  | YES | 0 | Neutral effect on stability |  | Power generation facility (towers, turbines, buried cables, substations, etc) | VERY HIGH
|  |  | Unknown | 2 | 2 | [8 empty] | Other infrastructure (water supply facility, telecomms facility) | HIGH
|  |  | Gritty / granular till with some clay | 2 | 2 |  | Gully reprofiling |  |  | YES | -1 | Slight increase in stability |  | Grazing / stock (sheep, deer, cattle) | MODERATE
|  |  | Granular or bedrock | 1 | 1 | [8 empty] | Arable (standing crops, productive land) | HIGH
[7 empty] | Gully damming / bunding |  |  | YES | 0 | Neutral effect on stability | Historic and Cultural Environment | YES
Geomorphology |  |  | Geomorphology | Peat Slide | Bog Burst | [8 empty] | NO
|  |  | Planar with pipes | 3 | 3 |  | Bare peat activities |  |  | YES | 0 | Neutral effect on stability
|  |  | Planar with pools | 2 | 3 | [8 empty] | Scheduled monument | HIGH
|  |  | Planar (no other features) | 2 | 2 |  | Scrub removal |  |  | YES | 0 | Neutral effect on stability |  | Other Nationally Important historic site/building | HIGH
|  |  | Undulating peat among rock outcrops | 1 | 1
|  |  | No geomorphology (forestry) | 0 | 0 |  | Forest to bog: tree removal |  |  | YES | 1 | Slight reduction in stability | CONSEQUENCE | RISK (LIKELIHOOD = MODERATE) | RISK (LIKELIHOOD = HIGH) | RISK (LIKELIHOOD = VERY HIGH)
|  |  | Slightly eroded (isolated gullies) | 1 | 1 | [7 empty] | VERY LOW | NEGLIGIBLE | NEGLIGIBLE | LOW
|  |  | Heavily eroded (extensive hagging) | 0 | 0 |  | Forest to bog: ridge and furrow blocking |  |  | YES | 0 | Neutral effect on stability | LOW | LOW | LOW | LOW
[13 empty] | MODERATE | LOW | MEDIUM | MEDIUM
Land Use |  |  | Land Use | Peat Slide | Bog Burst |  | Forest to bog: stump flipping |  |  | YES | 0 | Neutral effect on stability | HIGH | MEDIUM | MEDIUM | HIGH
|  |  | Machine cutting | 3 | 2 | [7 empty] | VERY HIGH | MEDIUM | HIGH | HIGH
|  |  | Hand cutting (turbary) | 1 | 2 |  | Forest to bog: stump flipping & brash |  |  | YES | -1 | Slight increase in stability
|  |  | Burning (shallow cracking) | 1 | 1 | [7 empty] | Qualitative descriptions of post-restoration risk
|  |  | Burning (deep cracking) | 2 | 2 |  | Forest to bog: stump flipping, brash & stem |  |  | YES | -2 | Increase in stability | NEGLIGIBLE | Given that risk has been calculated to be NEGLIGIBLE, restoration may continue as planned.
|  |  | Other land use | 0 | 0 | [7 empty] | LOW | Given that risk has been calculated to be LOW, restoration may continue as planned.
[13 empty] | MEDIUM | Given that risk has been calculated to be MEDIUM, a change in restoration technique should be considered (see below) or the site should be split into smaller units and re-assessed.
[7 empty] | Qualitative descriptions of post-restoration likelihood | [5 empty] | HIGH | Given that risk has been calculated to be HIGH, restoration proposals should be revised or parked (see below).
Forestry |  |  | Forestry | Peat Slide | Bog Burst |  | VERY LOW | very unlikely given the proposed restoration techniques
|  |  | Afforested, rows aligned | 1 | 1 |  | LOW | unlikely given the proposed restoration techniques |  |  |  |  | Mitigation
|  |  | Afforested, rows oblique | 2 | 2 |  | MODERATE | possible, given the proposed restoration techniques, A CONSEQUENCE ASSESSMENT IS REQUIRED |  |  |  |  | MEDIUM | Alternative restoration proposals may represent a lower risk. Consider modifying the techniques in STEP 2 until a risk of LOW or NEGLIGIBLE is calculated. If a lower risk cannot be calculated by changing restoration proposals, consider subdividing the site so that the factors controlling likelihood vary between areas.
|  |  | Deforested, rows aligned | 2 | 2 |  | HIGH | likely, given the proposed restoration techniques, A CONSEQUENCE ASSESSMENT IS REQUIRED |  |  |  |  | HIGH | Ground conditions suggest significant potential for instability both under natural conditions and as modified by restoration. Significant changes to restoration proposals will be required to reduce risks to acceptable levels.
|  |  | Deforested, rows oblique | 3 | 3 |  | VERY HIGH | very likely, given the proposed restoration techniques, RESTORATION IS NOT ADVISED
|  |  | Not afforested | 0 | 0
Slope Form |  |  | Slope Form | Peat Slide | Bog Burst
|  |  | Convex | 2 | 3
|  |  | Concave | 1 | 1
|  |  | Undulating | 1 | 1
|  |  | Rectilinear | 3 | 2
Drainage |  |  | Drainage | Peat Slide | Bog Burst
|  |  | Aligned to contour | 3 | 3
|  |  | Oblique to contour | 2 | 2
|  |  | Aligned to slope | 1 | 1
|  |  | Not drained | 0 | 0
Qualitative description of landslide at the site
|  | Top score | Description (to appear in Cell H137)
|  | 8 | VERY LOW | MINOR INSTABILITY | MINOR INSTABILITY | very unlikely given the baseline conditions observed over the restoration area
|  | 13 | LOW | MINOR INSTABILITY | MINOR INSTABILITY | unlikely given the baseline conditions observed over the restoration area
|  | 19 | MODERATE | PEAT SLIDE | BOG BURST | possible, given baseline conditions and the occurrence of a triggering event (e.g. intense rainfall, pipe collapse, adverse loading) somewhere within the restoration area
|  | 22 | HIGH | PEAT SLIDE | BOG BURST | likely, given baseline conditions and the occurrence of a triggering event (e.g. intense rainfall, pipe collapse, adverse loading) somewhere within the restoration area
|  |  | VERY HIGH | PEAT SLIDE | BOG BURST | very likely, given baseline conditions and the occurrence of a triggering event (e.g. intense rainfall, pipe collapse, adverse loading) somewhere within the restoration area
Type of peat |  |  | Fibrous
Pseudo-fibrous
Amorphous
FOS Calculation
|  |  | Amorphous |  | Pseudo-fibrous |  | Fibrous
|  |  | H10 |  | H8 - H6 |  | H3 - H5
|  |  | Low Estimate | High Estimate | Low Estimate | High Estimate | Low Estimate | High Estimate
| c' | kPa | 0 | 2 | 2 | 3 | 3 | 5
| φ' | ° | 20 | 25 | 25 | 30 | 30 | 35
| γ | kN/m3 | 10 | 10.5 | 10 | 10.5 | 10 | 10.5
FOS Explanation
This means that the site averaged conditions are not stable, and there is a high likelihood that some parts of the site will be unstable.
This means that the site averaged conditions may not be stable, given the uncertainty in input parameters.
This means that while the site averaged conditions indicate stability, there is reasonable likelihood that some parts of the site will be marginally stable.
This means that the site averaged conditions indicate stability and that any areas of marginal stability will be very localised, if present.
| Type of Peat |  | von Post | Description
| Fibrous |  | H3 - H5 | Plant remains clearly recognisable and retain some tensile strength. Water and no solids on squeezing.
| Pseudo-fibrous |  | H6 - H8 | Mixture of fibres and amorphous paste. Turbid water and <50% solids on squeezing.
| Amorphous |  | H10 | No recognisable plant remains, mushy consistency. Paste and >50% solids on squeezing.